## Use Case
|  | 107 |  |  |  | Status |  |  |  | Effort - Wok Days
UC Category | Actor | UC Number | Use Case | Relative Size | Business Priority | Use Case Complete | Func Design Complete | Dev Complete | Test Complete | Use Case Days | Func Design Days | Dev Days | Test Days | Flows and Notes (flows have a priority if the flow does not have the same priority as the use case) | Notes | Change Log | use case version refactor
Authentication | Provider Enroller | 15 | UC015_Provider_Enroller_Register | Small | Must Have | Y | Y |  |  | 0 | 0 | 7 | 1 | MF: Register MF: Update registration information |  | 2015-02-06: Added update flow to this use case, removed use case 82
Authentication | User | 14 | UC014_User_Login | Small | Must Have | Y | Y |  |  | 0 | 0 | 7 | 1 | Login
Authentication | User | 16 | UC016_User_Manage_Password | Small | Must Have | Y | Y |  |  | 0 | 0 | 7 | 1 | Reset password Change reset password Change password (should have)
Authentication | Provider Enroller | 94 | Launch from MN-ITS | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1 |  | There is work here to be done by the MN-ITS team.
Organization Application | System | 86 | UC086_User_View_Field_Change_History | Small | Must Have | Y |  |  |  | 0 | 2 | 7 | 1 | MF: View field change history
Organization Application | System | 19 | UC019_Application_State | Small | Must Have | Y |  |  |  | 0 | 2 | 7 | 1 |  | This is really common to multiple flows but it will be developed first in the organization flow
Organization Application | Provider Enroller | 6 | UC006_PE_Manage_Application_Via_Portal_Login (PE Landing Page) | Medium | Must Have | Y | Y |  |  | 0 | 0 | 10 | 3 | Create non-PCA application View application Update in-process application Delete application View "in-MMIS" applications (could have) |  |  | version refactor complete
Organization Application | Provider Enroller | 5 | UC005_PE_Manage_Application_Via_MN-ITS_Login (PE Landing Page) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | MF: View application MF: Update in-process application MF: Update completed application MF: Application not found |  |  | version refactor needed
Organization Application | User | 2 | UC002_User_Manage_Applicant_Type | Small | Must Have | Y | Y |  |  | 0 | 0 | 7 | 1 | MF: Set applicant type AF: Update applicant type not "in MMIS" EF: Update applicant type "in MMIS" MF: View applicant type as read-only |  | 2016-02-15: Split into three (See UC081, UC082), refactored for version, removed business rules | version refactor complete
Organization Application |  | 82 | UC082_User_Manage_Organization_Unique_Identifier | Extra small | Must have | Y | [7 empty] | MF: Crerate/update unique identifier MF: View unique identifier |  | 2016-02-15: Created by splitting 002 | version refactor complete
Organization Application | User | 3 | UC003_User_Manage_Organization_Info | Small | Must Have | Y | Y |  |  | 0 | 0 | 7 | 1 | Enter/update organization information View organization information |  |  | version refactor needed
Organization Application | User | 1 | UC001_User_Manage_Organization_Contact_Info | Small | Must Have | Y | Y |  |  | 0 | 0 | 7 | 1 | Enter/update organization contact information Copy the user contact View organization contact information |  |  | version refactor needed
Organization Application | User | 9 | UC009_User_Manage_Facility_Location | Medium | Must Have | Y | Y |  |  | 0 | 0 | 10 | 3 | Create facility location Update facility location Delete facility location not "in MMIS" Close facility location Undo close facility location View facility locations |  |  | version refactor needed
Organization Application | User | 12 | UC012_User_Manage_Addresses | Small | Must Have | Y | Y |  |  | 0 | 0 | 7 | 1 | Create facility location address Update facility location address Note: May add flows for non-facilities in the future |  |  | version refactor needed supervising professional refactor needed
Organization Application | User | 17 | UC017_User_Manage_Organization_Healthcare_Services | Medium | Must Have | Y |  |  |  | 0 | 6 | 10 | 3 | MF: Add services AF: Update services not "in MMIS" AF: Delete service not "in MMIS" EF: Cannot delete service "in MMIS" AF: Update service "in MMIS" AF: Terminate service "in MMIS" EF: Cannot terminate service not "in MMIS" AF: Reinstate service "in MMIS" MF: View services |  |  | version refactor needed refactor needed for two issues noted in the UC refactor for issues from UC030
Organization Application | User | 21 | UC021_User_Manage_Organization_Waivered_Services | Medium | Must Have | Y |  |  |  | 0 | 6 | 10 | 3 | - Add waivered service, including qualifications - Update "in MMIS" - Update not "in MMIS" - Delete not "in MMIS" - Terminate "in MMIS" - Reactive terminated |  | 2015-01-22: Split use case into two, this one is for orgs, added one for individuals | version refactor needed
Organization Application | User | 13 | UC013_User_Manage_Organization_Service_Provider_Identifiers | Small | Must Have | Y |  |  |  | 0 | 2 | 7 | 1 | MF: Maintain provider identifiers AF: Create initial provider identifier AF: Create replacement provider identifier EF: Cannot create provider identifier AF: Update provider identifier not "in MMIS" EF: Cannot update provider identifier "in MMIS" AF: Delete replacement provider identifer not "in MMIS" MF: View provider identifier |  | 2015-01-21: Divided, new use is UC018 | version refactor needed
Organization Application | User | 11 | UC011_User_Manage_Affiliated_Individual_Providers | Medium | Must Have | Y |  |  |  | 0 | 6 | 10 | 3 |  |  |  | version refactor needed
Organization Application | User | 30 | UC030_User_Manage_PCPO_Supervising_Professional | Medium | Must Have | Y |  |  |  | 0 | 6 | 10 | 3 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Personal Care Professional Organizations are required to enter the name and credential of supervisor - the supervisor is not enrolled. |  | version refactor needed
Organization Application |  | 85 | UC085_User_Manage_PCPO_Biller | Medium | Must Have | Y |  |  |  | 0 | 6 | 10 | 3
Organization Application | User | 28 | User manages organization healthcare service credentials | Large | Must Have |  |  |  |  | 5 | 10 | 20 | 5 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Provider Type License Provider Type Specialty
Organization Application | User | 29 | User manages organization waivered service credentials | Large | Must Have |  |  |  |  | 5 | 10 | 20 | 5 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Facility Credentials Waiver Service Credentials Site Visit upload date fie ld must be included PCA Training Cert
Organization Application |  | 92 | User manage forms (download, complete, scan, and upload) |  | Must have
Organization Application |  | 90 | User Manage County Contracts |  | Must have
Organization Application |  | 91 | UC091_User agrees to assurance statements |  | Must have
Organization Application | User | 31 | Ownership Info | Large | Must Have |  |  |  |  | 5 | 10 | 20 | 5 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS)
Organization Application | User | 32 | User, working on a third party biller application, manages the providers that they bill on behalf of | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | This UC is not applicable to non-third party billers
Organization Application | User | 10 | UC010_User_Manage_Assigned_Billers | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create assigned biller View assigned biller Update assigned biller - not "in MMIS" Update assigned biller - "in MMIS" Delete assigned biller - not "in MMIS" Delete assigned biller - "in MMIS" | User manages their third party billers (the organizations that perform their billing) (this UC is not applicable to third party billers)
Org App | User | 33 | User view pdf summary (filenet report) | Medium | Should have | [8 empty] | View (Main)
Organization Application | User | 34 | User agrees to agreements and addendums | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Update (Main) Submit
Organization Application |  | 93 | user enters proof of application fees or uploads hardship exemption request form |  | Must have
Organization Application | User | 78 | User search and find legacy provider | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Searching for legacy providers will be done in a number of use cases | This is really common to multiple flows but it will be developed first in the organization flow
I-Non PCA Application |  | 81 | UC081_User_Manage_Individual_Unique_Identifier | Extra small | Must Have | Y |  |  |  | 0 | 1 | 3.5 | 0.5 |  |  | 2016-02-15: Created by splitting 002 | version refactor complete
I-Non PCA Application | User | 36 | User manages individual application information (name, contact information) | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1 | Create (Main) Update Duplicate SSN/NPI (Create/update)
I-Non PCA Application |  | 37 | User manage individual's initial NPI or UMPI | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1 |  |  | 2015-01-21: Added
I-Non PCA Application |  | 38 | Service agent manage individual's replacement NPI or UMPI | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1 |  |  | 2015-01-21: Added
I-Non PCA Application | User | 39 | User enters affiliations and can mark one as primary practice | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS)
I-Non PCA Application |  | 40 | If in private practice, user selects/enters addresses and manages other practice information (fiscal year end, remittance sequence, etc.) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  | Can be a primary practice or in private practice.
I-Non PCA Application |  | 41 | User manages addresses for an individual non-PCA application | Extra small | Must Have |  |  |  |  | 0.5 | 1 | 3.5 | 0.5 |  | May be combined with UC012. Uncertain if there is much unique here.
I-Non PCA Application | User | 43 | User enters healthcare services for the location (no NPI/UMPI) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS)
I-Non PCA Application |  | 44 | User enters waivered services and qualifications (no NPI/UMPI) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
I-Non PCA Application |  | 49 | User enters healthcare service license credentials | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
I-Non PCA Application |  | 50 | User enters healthcare service specialty credentials | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
I-Non PCA Application |  | 51 | User enters waivered service credentials | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
I-Non PCA Application |  | 48 | User enters individual application's third party billers which will go on all legacy records generated for the application | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
I-Non PCA Application | User | 46 | User manages education (highest degree) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create Update System delete if no longer required | Whether or not education is required is dependent upon the healthcare service selected
I-Non PCA Application | User | 52 | User agrees to agreements and addendums (may reuse UC034) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Update (Main) Submit
I-Non PCA Application |  | 53 | User submits the individual application for approval (may reuse UC035) | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1
PCA Application |  | 54 | User manage PCA applications | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | - Can be invoked when in an appropriate application - Lists existing PCAs for the application - Initiate adding new PCA - Initiate updating existing PCA not in MMIS - Initiate updating existing PCA in MMIS - Initiate deleting PCA not in MMIS
PCA Application | User | 55 | User enters PCA personal Information | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS)
PCA Application |  | 57 | User manage training information | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
PCA Application | User | 58 | Background Study | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS)
PCA Application |  | 60 | User manage agreements | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
PCA Application |  | 61 | User submits individual PCA application | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1
Review | Service Agent | 4 | UC004_SA_Manage_Application (SA Landing Page) | Large | Must Have |  |  |  |  | 5 | 10 | 20 | 5 | Service Agent Create new application "Draft" Service Agent Create new PCA application "Draft" Service Agent find application Service Agent View application Service Agent Submit application "Draft to "Pending" Service Agent Unsubmit application "Pending" to "Draft" Service Agent Review application "Pending" to "Review" must "lock" application so others cannot edit and "unlock" later Service Agent Return to provider enroller "Review" to "Draft" Service Agent Set outcome "Review" to "Complete" Service Agent Update completed application "Complete" to "Draft" Service Agent Delete application not "in MMIS" Service Agent Assign to user that was created on behalf of | ok - 1/20/2015
Review | Provider Enroller | 79 | As a user I can view the status change history of an application (status, date/time, user) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  |  | 2015-02-02: A must have if the change log is the filenet report.
Review |  | 80 | As a service agent, while viewing the status change history, I can click on a row with a version in filenet and the system will display the application from filenet | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  |  | 2015-01-30: This is a must have assuming that the service agent uses the filenet report when reviewing changes. If MPSE has a "changes since last approval" report, this is lower priority.
Review |  | 64 | Service agent approve or deny each healthcare service | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1
Review |  | 65 | Service agent approve or deny each waivered service | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1
Review |  | 66 | Service agent approve or deny each healthcare service credential | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1
Review |  | 67 | Service agent approve or deny each waivered service credential | Small | Must Have |  |  |  |  | 1 | 2 | 7 | 1
Review |  | 68 | Service agent manages review notes | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
Review | User | 26 | System derives the legacy provider records | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  | Provider type rules are in the TaxonomyCrosswalk.xls
Review |  | 69 | Service agent overrides the derived legacy provider records | Extra large | Must Have |  |  |  |  | 8 | 14 | 80 | 7
Review |  | 97 | Consolidated 33 address
Review |  | 70 | Service agent manage screening date | Extra small | Must Have |  |  |  |  | 0.5 | 1 | 3.5 | 0.5
Review |  | 71 | System defaults categories of service (SA can change) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
Review | Service Agent | 72 | Service agent manages categories of service and major programs (these have spans) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  | Category of Service Major Programs
Review | Service Agent | 73 | Service agent manages specially, package service, and enhanced service codes (these do not have spans) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  | Specialty codes Package Service Codes Enhanced Service Codes
Review | Service Agent | 63 | For a PCA organization, the service agent determines if each of the associated individual PCAs is new or existing | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 | Create (new) Potential match exact match (screen doesn't show) | Name, SSN, DOB Variation of SSN multi data match
Review |  | 95 | Service agent completes review and declares outcome, for example: - send back to provider enroller with question - approve and send to MMIS | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
Review |  | 76 | Email provider enroller regarding application status - when approved - when notes added and sent back to provider enroller | Large | Must Have |  |  |  |  | 5 | 10 | 20 | 5
Misc |  | 84 | UC084_PE_Release_NPI | Small | Must have | Y |  |  |  | 0 | 2 | 7 | 1 | MF: Release NPI
Misc | Service Agent | 99 | Service agent can query applications by FEIN, SSN, NPI (and more) so that when a provider enroller cannot proceed due to a duplicate application error, the service agent can troubleshoot | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3
Misc | Service Administrator | 98 | As a user, when I click on the help icon, help for the page is displayed | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  | Someone needs to author the content, then system needs to "open" it.
Misc |  |  | System shall send correspondence to providers x days prior to their screening date (screening date is established during service agent review) | Medium | Must Have |  |  |  |  | 3 | 6 | 10 | 3 |  |  | 2015-01-30: It is a must have because it is the point of the system and a source of many problems now.
Technical | System | 101 | One time data conversion and load of provider information from MMIS | 2X large | Must Have |  |  |  |  | 21 | 18 | 160 | 9 |  | Technical specs
Technical | System | 74 | Interface to filenet (includes generating the PDF) | Extra large | Must Have |  |  |  |  | 8 | 14 | 80 | 7 | Success Fail | Technical specs
Technical | System | 75 | Interface to/from MMIS | 2X large | Must Have |  |  |  |  | 21 | 18 | 160 | 9 | Success Fail | Technical specs
Misc |  | 100 | SA assigns appliation to provider enroller it was started on behalf of
*** THIS LINE AND BELOW NOT IN TOTALS ***
*** OUT OF SCOPE ***
Organization Application |  | 87 | UC087_Admin_Manage_Assurance_Statements |  | Could have
Organization Application |  | 88 | UC088_User_Agree_To_HTML_Assurance_Statements |  | Could have
|  | 83 | System purges draft provider applications older than 1 year |  | Should have | [10 empty] | 2015-02-10: Out of scope for first release - not needed until 1 year after go-live
Misc SA | Service Administrator |  | Service administrator can manage service agent user records | Medium | Could have | [8 empty] | Create User Update user Delete user | Delete this UC if there is someone they email when a service agent or service administrator is added/changed/deleted | 2015-02-02: SA will email requests to others.
PCA App |  | 59 | System displays individual PCA application summary | Medium | Should have | [10 empty] | 2015-01-30: Priority set to "should have" assuming that the filenet report is implemented and the provider enroller has access to the report.
I-Non PCA App |  | 47 | System displays individual non-PCA application summary | Medium | Should have | [10 empty] | 2015-01-30: Priority set to "should have" assuming that the filenet report is implemented and the provider enroller has access to the report.
Review |  | 62 | Service agent review changes made to application since last approval (dependent upon UC081) | Medium | Should have | [8 empty] | - Change report not available until application is in MMIS - Report showing differences from last approved application |  | 2015-01-30: Priority changed to "should have". Assumption is that the service agent could compare the filenet reports for the last approved application and the application currently under review.
Misc SA | Service Administrator | 104 | Service administrator manages agreements, indicating if they are required, optional, or not needed | Medium | Should have | [8 empty] | Create Update |  | 2015-01-30: Priority set to "Should have" because service agent can contact IT each time a change is required. Need to quantify frequency of changes…
Misc SA | Service Agent |  | Change of Ownership Approval | Large | Should have | [8 empty] | provider keeps npi of old owner, provider gets new npi provider has an umpi and tax id changes provider has an umpi and tax id stays the same | if provider keeps npi of old owner, we change fein and update record if provider gets new npi we term out old record and create a new one if provider has an umpi and tax id changes we term and create a new record if provider has an umpi and tax id stays the same we update the record https://edocs.dhs.state.mn.us/lfserver/Public/DHS-5550-ENG | 2015-01-30: Priority changed to "should have". Appears that service agent may be able to make changes necessary through the existing functionality and not required "special" features. May need a small feature related to referencing the seller and acquirer for MMIS (needs investigation-could be that the field is not used in MMIS).
Misc User |  |  | User manage addresses | Medium | Should have | [8 empty] | CRUD of addresses for an application - have limited features from facility location addresses. May only be for organizations? |  | 2015-01-30: Provider enroller can edit address where it is used rather than via a global address manager (for an application)
Misc SA |  | 103 | User can perform and NPI query so that organizations who have instructed their individuals to enroll don't need to constantly call to see if the individual has enrolled | Medium | Should have | [10 empty] | 2015-01-30: Priority set to "Should have" because provider enrollers can continue calling as they are currently doing.
Misc User | User |  | Change of Ownership Initiation | Medium | Should have | [8 empty] | https://edocs.dhs.state.mn.us/lfserver/Public/DHS-5550-ENG |  | 2015-01-30: Priority changed to "should have". Can be initiated through a phone call or email.
Screening Schedule |  |  | Service agent can review a list of providers with legacy records past the screening date with applications that have not been submitted and choose to "pend" legacy records | Large | Should have | [10 empty] | 2015-01-30: Priority set to "Should have" because if the screening date is in MMIS the data warehouse can be leveraged.
Org App | User | 96 | System displays organization application summary (in a nice html page with links to jump to appropirate page to edit data that needs to be changed) | Medium | Should have | [8 empty] | View (Main) |  | 2015-01-30: Priority set to "should have" assuming that the filenet report is implemented and the provider enroller has access to the report.
Misc |  | 102 | System auto approve certain application, such as a phone number, email, or fax number change | Large | Should have
Out of scope |  |  | Effective date healthcare services with a begin date and end date | Small | Won’t have | [8 empty] | No UI to enter/change the begin/end date Don't allow to selected before begin date or after end date Display existing after end date | Would allow provider enroller to specify what date the service is available for use (begin date) and the date it can no longer be added to application (end date). See note in UC017. | 2015-01-21: Added
Out of scope |  |  | Effective date waivered services with a begin date and end date | Small | Won’t have | [8 empty] | No UI to enter/change the begin/end date Don't allow to selected before begin date or after end date Display existing after end date | Angie?
Out of scope | User |  | Change Log | Large | Won’t have | [8 empty] | Displays: Who, date/time, table fields, old, new | My understanding is that if we archive copies of each approved application to filenet, a change log is not required.
Out of scope |  | 105 | System calculates application fees that must be paid prior to submitting
Out of scope |  | 106 | Service Admin manage relationship between assurance statement and service(s)
*** TO BE DELETED ***
Out of scope | Service Agent |  | Rules Override | Medium | Won’t have | [8 empty] | This needs to be more specific. Which rules can be overridden and by whom? For example, ability for service agent to override the rule requiring that the SSN be unique because the user is enrolling as an individual and a organization (sole proprietor). | Determined that overrides will be part of each use case so this is not needed
Out of scope | System |  | MN-ITS registration letters to unregistered providers | Medium | Won’t have | [8 empty] | Purpose: to stop the Helpdesk from being flooded with calls. Follow up with MN-ITS team re: allowing non-Pay-To providers to register. | Business task - move to different list (Angie added to her list, be nice if on the project plan)

## Use Case Effort
| Work by Category Shown in Total Days per Categroy |  |  |  | Work by Category Shown in Total Hours per Categroy
Category -2/2/15 | Business Requirements | Functional Design | Technical Development | Testing | Business Requirements | Functional Design | Technical Development | Testing
Extra Small | 0.5 | 1 | 3.5 | 0.5 | 4 | 8 | 28 | 4
small | 1 | 2 | 7 | 1 | 8 | 16 | 56 | 8
medium | 3 | 6 | 10 | 3 | 24 | 48 | 80 | 24
large | 5 | 10 | 20 | 5 | 40 | 80 | 160 | 40
Extra large | 8 | 14 | 80 | 7 | 64 | 112 | 640 | 56
2X large | 21 | 18 | 160 | 9 | 168 | 144 | 1280 | 72
Category 1/26/15 | Business Requirements | Functional Design | Technical Development | Testing
Extra Small | 1.5 | 0.5 | 3.5 | 0.5
small | 3 | 1 | 7 | 1
medium | 6 | 3 | 10 | 3
large | 15 | 5 | 20 | 5
Extra large | 40 | 7 | 80 | 7
2X large | 80 | 9 | 160 | 9

## PivotTable-Work
Row Labels | Sum of Use Case Days | Sum of Func Design Days | Sum of Dev Days | Sum of Test Days
Authentication | 1 | 2 | 28 | 4
I-Non PCA Application | 34.5 | 70 | 135 | 35
Misc | 9 | 20 | 37 | 10
Organization Application | 30 | 96 | 229 | 58
PCA Application | 16 | 32 | 57 | 16
Review | 49.5 | 97 | 241.5 | 48.5
Technical | 50 | 50 | 400 | 25
(blank)
Grand Total | 190 | 367 | 1127.5 | 196.5

## PivotTable-Count
Row Labels | Count of Use Case | Count of Use Case Complete
Must Have | 73 | 20
(blank)
Grand Total | 73 | 20

## Use Case Burndown
Count of Use Cases
5 days ending | Beginning balance | Adds and removals | Complete | Ending balance | Notes
2015-01-13 | 85 |  | -9 | 76 | Beginning counts
2015-01-20 | 76 | 0 | -2 | 74 | Completed: - UC009_User_Manage_Facility_Location - UC012_User_Manage_Addresses
2015-01-27 | 74 | -1 | -4 | 69 | Completed: - UC017_User_Manage_Organization_Healthcare_Services - UC021_User_Manage_Organization_Waivered_Services - UC022_User_Manage_Organization_Waivered_Service_Initial_NPI_or_UMPI - UC018_Manage_Organization_Healthcare_Service_Replacement_NPI_or_UMPI Removed waivered service qualification use case, it is included in 021
2015-02-03 | 69 | -11 | -2 | 56 | Completed: - UC019_Application_State - UC011_User_Manage_Affiliated_Individual_Providers Prioritization resulted in removal of 11 use cases
2015-02-10 | 56 | -1 | -1 | 54 | - Completed "UC082 Updated registration information" by adding flow to "UC015 Provider enroller register" - Completed UC030_User_Manage_PCPO_Supervising_Professional - Split UC002 into UC002, UC081, and UC082 (all are complete) - Added "UC081 application versioning" and removed during the week (not needed because it is part of many other use cases-should add to business requirements doc)
2015-02-17 | 54 | 0 | 0 | 54 | - Added and completed UC084_PE_Release_NPI - Removed completed UC018 Replacement NPI
2015-02-24 | 54 | 1 | -2 | 53 | - Removed UC027 Add additional information based upon service-fields added to UC017 (which was already complete) - Added UC085 PCA Billing Person and completed - Added UC086_User_View_Field_Change_History
Totals | 85 | -12 | -20 | 53
Pivot table check values |  | 73 | -20 | 53
Error if not zero |  |  | 0 | 0

## List
Status | Priority | Size
WIP | Must have | Extra small
Review | Should have | Small
Refactor | Could have | Medium
Complete | Won’t have | Large
Extra large
2X large

## Definitions-Old (hidden)
Status
WIP | Work in Progress - Task is assigned and being worked on
Review | Task is out for team reivew and approval. Angie will determine if a business team walkthrough is required
Done | Approved by all areas to move forward

## Use Case-Old (hidden)
Use Case
Priority Order | UC Category | Actor | Use Case | Flow | Notes | Relative Size | Business Priority | Gate | BA Status | BA | Approval Date | Func Status | Func | Approval Date | Tech Status | Tech | Approval Date | Func | Tech | Functional Design
1 | Common | Provider Enroller | UC015_Provider_Enroller_Register | Register |  | Small | Must Have | Tech | Approved | Karen |  | Approved | Wendy | 2014-12-22 | WIP | Will |  | Steve |  | FDP0020_Register_Email_Username_Page FDP0024_Register_Security_Page FDP0028_Register_Confirm_Page
2 | Common | User | UC014_User_Login | Login |  | Small | Must Have | Tech | Approved | Karen |  | Approved | Wendy | 2014-12-23 | WIP | Will |  | Steve |  | FDP0010_Login_Page
3 | Common | User | UC016_User_Manage_Password | Reset password |  |  | Must Have | Tech | Approved | Karen |  | Approved | Func |  | WIP | Will |  | Steve |  | FDP0030_ResetPW_Username_Page FDP0034_ResetPW_Challenge_Page FDP0038_ResetPW_Confirm_Page
4 | Common | User | UC016_User_Manage_Password | Change reset password |  |  | Must Have | Tech |  |  |  | Approved | Func | [6 empty] | FDP0031_Retrieve_Username_Page FDP0034_ResetPW_Challenge_Page FDP0038_ResetPW_Confirm_Page
| Common | User | UC016_User_Manage_Password | Change password |  |  | Should Have | Tech |  |  |  | Approved | Func | [6 empty] | FDP0032_Retrieve_Username_Confirmation_Page FDP0034_ResetPW_Challenge_Page FDP0038_ResetPW_Confirm_Page
6 | Maintenance | Provider Enroller | UC006_PE_Manage_Application_Via_Portal_Login | MF: Create non-PCA application |  |  | Must Have | Tech | Approved | David |  | Approved | Func |  |  |  | Steve | Steve |  | FDP0014_Must_Change_Password_Page
7 | Maintenance | Provider Enroller | UC006_PE_Manage_Application_Via_Portal_Login | MF: View application |  |  | Must Have | [5 empty] | Func
8 | Maintenance | Provider Enroller | UC006_PE_Manage_Application_Via_Portal_Login | MF: Update in-process application |  |  | Must Have |  |  |  |  | Approved | Func | [6 empty] | FDP0040_Provider_Enroller_Home_Page
9 | Maintenance | Provider Enroller | UC006_PE_Manage_Application_Via_Portal_Login | MF: Delete application |  |  | Must Have |  |  |  |  | Approved | Func | [6 empty] | FDP0040_Provider_Enroller_Home_Page
| Maintenance | Provider Enroller | UC006_PE_Manage_Application_Via_Portal_Login | MF: View "in-MMIS" applications |  |  | Could Have |  |  |  |  | Approved | Func | [6 empty] | FDP0040_Provider_Enroller_Home_Page
11 | Common | User | UC002_User_Manage_Applicant_Type_And_Identifier | MF: Add Applicant Type and Identifier(s) |  |  | Must Have | Tech | Approved | Derik |  |  | Func |  |  |  |  | Steve |  | FDP0040_Provider_Enroller_Home_Page
12 | Common | User | UC002_User_Manage_Applicant_Type_And_Identifier | AF: Update Applicant Type - not "in MMIS" |  |  | Must Have | [5 empty] | Func
13 | Common | User | UC002_User_Manage_Applicant_Type_And_Identifier | AF: Update Applicant Type - "in MMIS" |  |  | Must Have |  |  |  |  | Approved | Func | [6 empty] | FDP0050_Applicant_Type_Identifier_Page
14 | Common | User | UC002_User_Manage_Applicant_Type_And_Identifier | AF: View Applicant Type and Identifier(s) |  |  | Must Have |  |  |  |  | Approved | Func | [6 empty] | FDP0050_Applicant_Type_Identifier_Page
15 | Org | User | UC003_User_Manage_Organization_Info | MF: Enter/update organization information |  | Small | Must Have | Tech | WIP | Karen |  | Approved | Func | [6 empty] | FDP0050_Applicant_Type_Identifier_Page
16 | Org | User | UC003_User_Manage_Organization_Info | MF: View organization information |  | Small | Must Have |  |  |  |  | Approved | Func | [6 empty] | FDP0050_Applicant_Type_Identifier_Page
17 | Org | User | UC001_User_Manage_Organization_Contact_Info | MF: Enter/update organization contact information |  | Medium | Must Have | Tech | Approved | David |  | Approved | [5 empty] | Steve |  | FDP0060_Organization_Information_Page
18 | Org | User | UC001_User_Manage_Organization_Contact_Info | MF: View organization contact information |  |  | Must Have |  |  |  |  | Approved | [7 empty] | FDP0060_Organization_Information_Page
19 | Common | User | UC012_User_Manage_Addresses | Create, did not check any affiliation (Main) Affiliation with use addresses Update |  | Large | Must Have | Bus | WIP | Derik |  | Approved | [7 empty] | FDP0060_Organization_Information_Page
20 | Org | User | UC009_User_Manage_Facility_Location | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) Term location Un-Term location | Need CRUD for NPI for location. Need ability to end location - need effective dates for each location. Entry of location requires an effective date. User must pick reason when closing location/entering end date. (Angie to provide reasons). User can un-term a termed location. Terming location results in terming all associated MMIS records with that NPI/location. Location should not be entered twice - can be associated with multiple NPIs/UMPIs | Large | Must Have | Func | WIP | Karen |  | Approved | [7 empty] | FDP0060_Organization_Information_Page
21 | Org | User | UC011_User_Manage_Individual_Member_Info | Create individual member info |  | Medium | Must Have | Bus | WIP | Derik
22 | Org | User | UC011_User_Manage_Individual_Member_Info | View individual member info |  |  | Must Have
23 | Org | User | UC011_User_Manage_Individual_Member_Info | Update individual member info - not "in MMIS" |  |  | Must Have
24 | Org | User | UC011_User_Manage_Individual_Member_Info | Update individual member - "in MMIS" |  |  | Must Have
25 | Org | User | UC011_User_Manage_Individual_Member_Info | Delete indivudla member - not "in MMIS" |  |  | Must Have
26 | Org | User | UC011_User_Manage_Individual_Member_Info | Delete individual member - "in MMIS" |  |  | Must Have
27 | Org | User | UC017_User_Services | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Taxonomy code selection. | Large | Must Have |  | WIP | Karen
28 | Common | User | Waiver Services | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Different services by provider type | Large
29 | Org | User | UC013_Manage_Organization_Provider_Identifier | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Alternate Flow for entry of Non-NPI. System should display tree of location/service info for each. | Large | Must Have |  | WIP | Mary
30 | Common | User | UC018_Map_MPSE_Addresses_To_MMIS | MF: Map MPSE addresses to MMIS |  | Medium | Must Have | Bus | WIP | Derik
31 | Common | User | Derive Provider Type
32 | Org | User | Provider Type Info | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Facility ID, ISD#, PCA Billing Person, Medicare ID number, etcetera | Medium
33 | Common | User | Credentials | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Provider Type License Provider Type Specialty Facility Credentials Waiver Service Credentials Site Visit upload date fie ld must be included. PCA Training Cert | Large
34 | Org | User | Supervising Professional Info | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) |  | Medium
35 | Org | User | Ownership Info | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) |  | Medium
36 | Org | User | Billing Org Pay-To Setup | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) |  | Medium
37 | Common | User | UC010_User_Manage_Assigned_Billers | Create assigned biller |  | Medium | Must Have |  | Review | Mary
38 | Common | User | UC010_User_Manage_Assigned_Billers | View assigned biller |  |  | Must Have
39 | Common | User | UC010_User_Manage_Assigned_Billers | Update assigned biller - not "in MMIS" |  |  | Must Have
40 | Common | User | UC010_User_Manage_Assigned_Billers | Update assigned biller - "in MMIS" |  |  | Must Have
41 | Common | User | UC010_User_Manage_Assigned_Billers | Delete assigned biller - not "in MMIS" |  |  | Must Have
42 | Common | User | UC010_User_Manage_Assigned_Billers | Delete assigned biller - "in MMIS" |  |  | Must Have
43 | Common | User | Summary | View (Main) |  | Large
44 | Common | User | Agreements | Update (Main) Submit |  | Medium
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Create new application "Draft" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Create new PCA application "Draft" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent View application |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Submit application "Draft to "Pending" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Unsubmit application "Pending" to "Draft" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Review application "Pending" to "Review" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Return to provider enroller "Review" to "Draft" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Set outcome "Review" to "Complete" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Update completed application "Complete" to "Draft" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Delete application Must not be "in MMIS" |  |  |  |  | Review
| Maintenance | Service Agent | UC004_SA_Manage_Application | Service Agent Assign to user that was created on behalf of |  |  |  |  | Review
| Common | Service Agent | Change of Ownership Approval | provider keeps npi of old owner, provider gets new npi provider has an umpi and tax id changes provider has an umpi and tax id stays the same | if provider keeps npi of old owner, we change fein and update record if provider gets new npi we term out old record and create a new one if provider has an umpi and tax id changes we term and create a new record if provider has an umpi and tax id stays the same we update the record https://edocs.dhs.state.mn.us/lfserver/Public/DHS-5550-ENG
| Common | User | Provider Lookup | Main |  | Small
| Common | Service Agent | Rules Override | Main |  | Medium
| Dashboard | Service Agent | Change/Modify NPI/UMPI | Change NPI at global level Change NPI/UMPI at location level
| Dashboard | Service Agent | Service Agent Home | Main new application | launch the PCA maintenance for organization. Initiate review of application, with grid of pending - stamp specialist name on application when opened for review. | Large
| Dashboard | Service Agent | Application query | Main |  | Small
| Functions | Service Agent | Associate Pre-MN-ITS records with Public Portal login
| Review | Service Agent | Legacy Record Review-with spans | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Category of Service Major Programs | Large
| Review | Service Agent | Legacy Record Review-without spans | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Specialty codes Package Service Codes Enhanced Service Codes | Large
| Review | Service Agent | PCA match | Create (new) Potential match exact match (screen doesn't show) | Name, SSN, DOB Variiation of SSN multi data match | Large
| Review | Service Agent | Reviewing changes | Approved changes (main) edit (steps through all forms) |  | Large
| Review | Service Agent | Service Review | Approve or deny services (Main) | Approve/deny all by location and level 1 taxonomy. Level 2 taxonomy approved individually. Level 3 not shown. | Large
| Common | System | Status | Create (Main) Read Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) |  | Small
| Maintenance | Provider Enroller | UC005_PE_Manage_Application_Via_MN-ITS_Login | MF: Create PCA application |  |  |  |  | Review
| Maintenance | Provider Enroller | UC005_PE_Manage_Application_Via_MN-ITS_Login | MF: View application |  |  |  |  | Review
| Maintenance | Provider Enroller | UC005_PE_Manage_Application_Via_MN-ITS_Login | MF: Update in-process application |  |  |  |  | Review
| Maintenance | Provider Enroller | UC005_PE_Manage_Application_Via_MN-ITS_Login | MF: Update completed application |  |  |  |  | Review
| Maintenance | Provider Enroller | UC005_PE_Manage_Application_Via_MN-ITS_Login | MF: Application not found |  |  |  |  | Review
| Common | Provider Enroller | Launch from MN-ITS | Main |  | Small
| I-Non PCA | User | Affiliations | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) | Also includes PCA affiliations but a separate screen. | Medium
| I-Non PCA | User | Education | Create (Main) Update | Must be removed if no longer needed | Medium
| I-Non PCA | User | Individual Info | Create (Main) Update Duplicate SSN/NPI (Create/update) | Cannot change Practice Type once in MMIS If not in MMIS they user has to start over if practice type is changed | Medium
| I-Non PCA | User | Practice Info | Private Practice (main) Primary practice (nothing to enter) Update | Do not do unique test on FEIN | Small
| I-Non PCA | User | Services | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) |  | Large
| PCA | User | Personal Info | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) |  | Medium
| PCA | User | Background Study | Create (Main) Update (in MMIS) Update (Not in MMIS) Delete (in MMIS) Delete (not in MMIS) |  | Medium
| Common | User | Change Log | View (Main) | Displays: Who, date/time, table fields, old, new | Large
| Functions | Service Administrator | Help Topics | Create Update delete |  | Medium
| Functions | Service Administrator | Maintain System User | Create User Update user Delete user | System inserts 1st Service Admin | Medium
| Functions | Service Administrator | Maintaining Agreements | Create Update |  | Medium
| Functions | Service Administrator | Screening Schedule | Create Update |  | Small
| Common | User | Change of Ownership Initiation |  | https://edocs.dhs.state.mn.us/lfserver/Public/DHS-5550-ENG
| Common | User | User Options | Collection of many |  | Medium
| Common | Provider Enroller | Self manage user information | CRUD the information a user enters during registration
| Common | User | Request NPI/UMPI change | Main
| Common | User | NPI/Location/Service Type Tree
| Dashboard | Provider Enroller | Account |  | Login information for the Portal, and not the enrollment
| Dashboard | Provider Enroller | Provider Enrollment History
| Dashboard | User | Delete provider application | Not in MMIS In MMIS |  | Small
| Common | User | UC019_Remittance_ sequence | View default Update | selection sequence view for remittance advice | Small
| Technical | System | Audit |  | Open Update (before/after) close without an update # of records # of records approved Both internal and external | Large
| Technical | System | Data conversion |  | Technical specs | Large
| Technical | System | Effective dating |  | Technical specs | Large
| Technical | System | Interface to filenet | Success Fail | Technical specs | Large
| Technical | System | Interface to MMIS | Success Fail | Technical specs | Large
| Technical | System | MN-ITS registration letters to unregistered providers | Success Fail | Purpose: to stop the HelpDesk from being flooded with calls. Follow up with MN-ITS team re: allowing non-Pay-To providers to register. | Medium

## Functional Design-Old (hidden)
Functional Design | Assigned | Status
SFDP0001_Guide | Wendy | WIP
FDP0020_Register_Email_Username_Page | Wendy | Approved
FDP0024_Register_Security_Page | Wendy | Approved
FDP0028_Register_Confirm_Page | Wendy | Approved
FDP0010_Login_Page | Wendy | Approved
FDP0030_ResetPW_Username_Page | Steve | Approved
FDP0034_ResetPW_Challenge_Page | Steve | Approved
FDP0038_ResetPW_Confirm_Page | Steve | Approved
FDP0014_Change_Password_Page | Steve | Approved
FDP0031_Retrieve_Username_Page | Steve | Approved
FDP0032_Retrieve_Username_Confirmation_Page | Steve | Approved
FDP0040_Provider_Enroller_Home_Page | Steve | Approved
FDP0050_Applicant_Type_Identifier_Page | Steve | Approved
FDP0060_Organization_Information_Page | Steve | Approved

## Technical-Old (hidden)
Technical Tasks
Component | Goal | Task | Subtask | Status
User registration web app
Tech docs
Update and create technical docs for the user self-registration app
|  |  | mmis/architecture/MMIS-Build-Dependencies.vsd | Done
|  |  | mmis/architecture/MMIS-Source-Organization.vsd | Done
|  |  | mmis/architecture/Naming-Conventions.docx | Done
|  |  | (new) ur/design/Components-Architecture.vsd | Done
|  |  | (new) ur/design/ArchitecturalTiers-UserRegistrationWebApp.vsd | Done
|  |  | (new) ur/design/High-Level-Design.docx | in progress
Create user self-registration app
|  | source tree structure |  | Done
|  | build |  | in progress
|  | spring mvc setup |  | in progress
|  | spring security |  | in progress
sitemesh setup
sitemesh template for its pages
create first page

## Definitions
Meaning | Description
Must have | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
Should have | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
Could have | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
Won't have | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## Sheet1
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6 | 6
9 | 9
10 | 10
11 | 11
12 | 12
13 | 13
14 | 14
15 | 15
16 | 16
17 | 17
19 | 19
21 | 21
26 | 26
28 | 28
29 | 29
30 | 30
31 | 31
32 | 32
33 | 33
34 | 34
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
43 | 43
44 | 44
46 | 46
47 | 47
48 | 48
49 | 49
50 | 50
51 | 51
52 | 52
53 | 53
54 | 54
55 | 55
57 | 57
58 | 58
59 | 59
60 | 60
61 | 61
62 | 62
63 | 63
64 | 64
64 | 65
65 | 66
66 | 67
67 | 68
68 | 69
69 | 70
70 | 71
71 | 72
72 | 73
73 | 74
74 | 75
75 | 76
76 | 78
78 | 79
79 | 80
80 | 81
81 | 82
82 | 83
83 | 84
84 | 85
85 | 86
86 | 87
87 | 88
88 | 90
90 | 91
91 | 92
92 | 93
93 | 94
94